## Roadmap
Serevo WFM — Production Roadmap
Updated October 3, 2026 · Bergeron WFM Solutions
# | Feature | Status | Details | Priority | Category
Phase 1 — Data Layer & Storage
1.1 | PostgreSQL Database | ✅ Complete | SQLAlchemy ORM, 30+ models, Alembic migrations, Render managed Postgres | High | Foundation
1.2 | CSV / Excel Upload | ✅ Complete | 7 upload types: employees, forecast, requirements, accommodations, PTO, actuals, agent status | High | Foundation
1.3 | API Connection Manager | ✅ Complete | Full CRUD settings UI, test/sync/toggle, connector framework (base, registry, sync, wfm_legacy) | High | Foundation
1.4 | Manual Data Entry Forms | 🔶 Partial | Accommodation & PTO modals work; employee add exists but limited inline editing | Medium | Foundation
1.5 | Google Sheets Integration | ✅ Complete | gspread integration with save/test/disconnect; used as forecast data source | Medium | Foundation
Phase 2 — Auth & User Management
2.1 | Password-Based Login | ✅ Complete | Flask-Bcrypt hashing, demo accounts preserved, session-based auth | High | Foundation
2.2 | User Roles (Admin/Supervisor/Agent) | ✅ Complete | Three-tier system with decorators: login_required, admin_required, agent_required, supervisor_required | High | Foundation
2.3 | User Management UI | ✅ Complete | Admin page: create/edit/toggle-active users, employee auto-linking on creation | High | Foundation
2.4 | Session Security | 🔶 Partial | Session-based auth works; no CSRF protection or configurable session timeout yet | Medium | Foundation
2.5 | OAuth / SSO | ❌ Not Started | Designed for future swap — not needed for initial launch | Low | Foundation
Phase 3 — Table UX & Interactivity
3.1 | Column Sorting | ✅ Complete | table-utils.js: auto-detect numeric/date/text, asc/desc toggle on all tables | Medium | UX Polish
3.2 | Advanced Filters | ✅ Complete | TableFilter.init, .dropdown, .dateRange — text search, dropdown, and date range filters | Medium | UX Polish
3.3 | Conditional Formatting | 🔶 Partial | Status-based coloring in realtime templates; not a universal system across all tables | Low | UX Polish
3.4 | Pagination | ❌ Not Started | Queries use .limit() but no page/offset pagination for large datasets | Low | UX Polish
3.5 | Export to CSV/Excel | 🔶 Partial | Capacity export exists; no universal export buttons on all data tables | Medium | UX Polish
Phase 4 — Module Completion
4.1 | Demo Data in All Modules | ✅ Complete | All modules generate realistic demo data: portal, scheduling, forecasting, realtime, people | High | Core Features
4.2 | Employee Management (Add/Edit/Deactivate) | ✅ Complete | Full roster + profile pages, accommodation/PTO CRUD, skill assignments with proficiency | High | Core Features
4.3 | Scheduling Engine | ✅ Complete | 1585-line engine: greedy generation, coverage analysis, scoring, multi-day, rotation/fill-in | High | Core Features
4.4 | Forecasting Data Import | ✅ Complete | Historical data pipeline from CSV, API, and Google Sheets into normalized DB tables | High | Core Features
4.5 | Real-Time Data Feed | 🔶 Partial | Snapshot-on-demand via realtime engine; no live WebSocket or continuous polling yet | Medium | Core Features
Phase 5 — Polish & Go-Live
5.1 | Error Handling | 🔶 Partial | try/except in routes with flash messages; no custom 404/500 pages | Medium | Infrastructure
5.2 | Structured Logging | 🔶 Partial | logging.getLogger used in engines; no JSON logs or correlation IDs | Low | Infrastructure
5.3 | Automated Tests | ❌ Not Started | No tests/ directory or test files | Medium | Infrastructure
5.4 | Navigation Consistency | ✅ Complete | Shared base.html with consistent nav, sidebar, flash messages, mobile hamburger | Medium | Infrastructure
5.5 | Custom Domain | ❌ Not Started | Render deployment live; no custom domain configured yet | Low | Infrastructure
5.6 | Landing Page | 🔶 Partial | Template exists in legacy code; not fully wired as public marketing page | Low | Infrastructure
Phase 6 — Agent Self-Service Portal
6.1 | Agent Schedule View | ✅ Complete | My Schedule tab in portal + standalone page, week nav, date picker, today highlight | High | Competitive Feature
6.2 | Time-Off Requests | ✅ Complete | Submit/cancel PTO through portal; approval queue for managers | High | Competitive Feature
6.3 | Shift Bidding | ✅ Complete | ShiftPost/ShiftBid models; list/submit/cancel bids with demo data | High | Competitive Feature
6.4 | Shift Swapping | ✅ Complete | ShiftSwapRequest model; submit/accept/cancel swaps | High | Competitive Feature
6.5 | VTO / Overtime Sign-Up | ✅ Complete | VTOOTPost/VTOOTSignup models; list/signup/cancel with real-time updates | High | Competitive Feature
6.6 | Mobile PWA | ❌ Not Started | No manifest.json or service worker; portal is web-only | Medium | Competitive Feature
Phase 7 — Forecasting Engine
7.1 | Historical Data Pipeline | ✅ Complete | Ingest from CSV, API, Sheets into normalized time-series tables by interval | High | Competitive Feature
7.2 | Statistical Forecasting | ✅ Complete | Moving avg, weighted avg, Holt-Winters triple exponential smoothing; auto-select best method | High | Competitive Feature
7.3 | AI/ML Forecasting | ❌ Not Started | No scikit-learn/Prophet/neural net integration | Low | Competitive Feature
7.4 | Forecast Accuracy Tracking | ✅ Complete | MAPE, WMAPE, bias metrics with compute_accuracy | High | Competitive Feature
7.5 | Mid-Day Reforecasting | ❌ Not Started | No triggered reforecast based on actual vs. forecast variance | Medium | Competitive Feature
7.6 | What-If Scenario Planning | ✅ Complete | apply_what_if with volume/AHT percentage adjustments and scenario comparison | High | Competitive Feature
Phase 8 — Multi-Skill Scheduling
8.1 | Skill Proficiency Modeling | ✅ Complete | SkillMapping with 1–5 proficiency, priority, UI for assign/remove on profiles | High | Enterprise Feature
8.2 | Multi-Skill Demand Calculation | ✅ Complete | get_multi_skill_requirements splits demand proportionally by skill group | High | Enterprise Feature
8.3 | Constraint-Based Optimizer | 🔶 Partial | Greedy algorithm with skill/availability/accommodation constraints; no LP/CP solver | High | Enterprise Feature
8.4 | Schedule Scoring & Comparison | ✅ Complete | Multi-dimension scoring: coverage %, SL prediction, cost, preference satisfaction | Medium | Enterprise Feature
8.5 | Bulk Schedule Editing | ✅ Complete | Select multiple agents, apply same change; essential for volume spikes | Medium | Enterprise Feature
Phase 9 — Intraday & Advanced
9.1 | Intraday Schedule Optimization | ✅ Complete | Break moves, VTO offers, skill reassignment logic in intraday engine | High | Enterprise Feature
9.2 | RT Adherence Drill-Down | ✅ Complete | Per-agent adherence timeline with schedule vs. actual state comparison | High | Enterprise Feature
9.3 | Queue-Level Net Staffing | ✅ Complete | Required vs. scheduled vs. actual per queue with surplus/deficit indicators | High | Enterprise Feature
9.4 | Gamification & Engagement | ✅ Complete | Leaderboard with adherence points, badges, configurable metrics | Medium | Enterprise Feature
9.5 | Long-Range Capacity Planning | ✅ Complete | Multi-year projections with attrition, hiring lead times, what-if scenarios | Medium | Enterprise Feature
9.6 | Interaction Analytics Integration | ✅ Complete | Webhook receiver for external QM data; merged dashboard alongside schedule data | Medium | Enterprise Feature
9.7 | Coaching Session Management | ✅ Complete | CRUD for coaching sessions tied to performance; profile tab integration | Medium | Enterprise Feature

## Summary
Roadmap Summary by Phase
Phase | Complete | Partial | Not Started | Total | % Complete
Phase 1 — Data Layer & Storage | 4 | 1 | 0 | 5 | 80%
Phase 2 — Auth & User Management | 3 | 1 | 1 | 5 | 60%
Phase 3 — Table UX & Interactivity | 2 | 2 | 1 | 5 | 40%
Phase 4 — Module Completion | 4 | 1 | 0 | 5 | 80%
Phase 5 — Polish & Go-Live | 1 | 3 | 2 | 6 | 16.67%
Phase 6 — Agent Self-Service Portal | 5 | 0 | 1 | 6 | 83.33%
Phase 7 — Forecasting Engine | 4 | 0 | 2 | 6 | 66.67%
Phase 8 — Multi-Skill Scheduling | 4 | 1 | 0 | 5 | 80%
Phase 9 — Intraday & Advanced | 7 | 0 | 0 | 7 | 100%
TOTAL | 34 | 9 | 7 | 50 | 68%