## Roadmap
✓ | Phase | Item | Task | Details | Est. Effort | Status | Notes
☐ | Phase 1 | 1.1 | Add PostgreSQL database | Replace Google Sheets with Postgres via SQLAlchemy + Flask-Migrate. Tables: employees, accommodations, pto_entries, forecast_raw, requirements_raw, planning_units, schedules, users. | 2–3 weeks | Not Started
☐ |  | 1.2 | CSV / Excel upload | Admin drag-drop page to bulk-import employees, forecasts, or requirements. Parse with openpyxl, validate columns, preview before commit. |  | Not Started
☐ |  | 1.3 | API connection manager | Settings page for external API credentials (PeopleWare/Injixo). Store encrypted. Support manual pull + scheduled pulls. |  | Not Started
☐ |  | 1.4 | Manual data entry forms | Expand modals for employee add/edit and forecast manual entry. Each writes to Postgres. |  | Not Started
☐ |  | 1.5 | Keep Google Sheets option | Don't remove SheetSource — make it selectable alongside Postgres in settings. |  | Not Started
☐ | Phase 2 | 2.1 | Password-based login | Replace email allow-list with bcrypt-hashed passwords via Flask-Bcrypt. Keep demo accounts in DEMO_MODE. | 1 week | Not Started
☐ |  | 2.2 | User roles | Admin (full access), Manager (view + edit), Viewer (read-only). Store in users table, enforce with route decorators. |  | Not Started
☐ |  | 2.3 | User management UI | Admin page to invite users, edit roles, deactivate accounts. No self-registration. |  | Not Started
☐ |  | 2.4 | Session security | Session expiry (8h default), CSRF via Flask-WTF, secure cookie flags (httponly, samesite, secure). |  | Not Started
☐ |  | 2.5 | Future: OAuth / SSO | Design auth layer so Google OAuth or SAML can be added later without rewrite. |  | Not Started
☐ | Phase 3 | 3.1 | Column sorting | Clickable table headers for ascending/descending sort. Pure JS, all data tables. | 1 week | Not Started
☐ |  | 3.2 | Advanced filters | Filter dropdowns above each table: by LOB, date range, status. Extend roster pattern to all modules. |  | Not Started
☐ |  | 3.3 | Conditional formatting | Color-code cells by thresholds: red/yellow/green for SL targets, staffing shortages, adherence %. |  | Not Started
☐ |  | 3.4 | Pagination | Server-side pagination or virtual scroll for 100+ row tables (forecast raw, requirements raw). |  | Not Started
☐ |  | 3.5 | Export to CSV/Excel | Export buttons on every data table. Generate file server-side with openpyxl. |  | Not Started
☐ | Phase 4 | 4.1 | Wire demo data — all modules | Complete DemoSource integration for Scheduling, Forecasting, Real-Time so every page works in demo mode. | 2–3 weeks | Not Started
☐ |  | 4.2 | Employee management CRUD | Add/edit/deactivate employees on People page. Modal with name, ID, LOB, status, start date. |  | Not Started
☐ |  | 4.3 | Scheduling engine | Take requirements + availability + accommodations + PTO → shift assignments. Greedy algorithm to start. |  | Not Started
☐ |  | 4.4 | Forecasting data import | CSV upload of historical volume. Generate forecasts with Erlang C engine. Accuracy tracking. |  | Not Started
☐ |  | 4.5 | Real-time data feed | API polling or webhook for live data. 60s polling sufficient for launch. UI auto-refresh already built. |  | Not Started
☐ | Phase 5 | 5.1 | Error handling | Custom 404/500 pages. Try/except on all routes. /health checks DB connectivity. | 1–2 weeks | Not Started
☐ |  | 5.2 | Logging | Structured logging via Python logging module. Log imports, auth, errors. Pipe to Render/Papertrail. |  | Not Started
☐ |  | 5.3 | Tests | pytest in tests/ directory. Priority: auth, data import/export, API endpoints, demo fallback. |  | Not Started
☐ |  | 5.4 | Navigation consistency | Shared nav in base.html with active-state highlighting and mobile hamburger menu. |  | Not Started
☐ |  | 5.5 | Custom domain | Point domain at Render. SSL automatic. Update branding config. |  | Not Started
☐ |  | 5.6 | Landing page | Public page for Bergeron WFM Solutions: services, demo link, contact. Separate route or static site. |  | Not Started
Total estimated timeline: 7–10 weeks